## Sheet1
Name: Sean Russell
Section Number: 3
Major Project Description: Chess
Due Date: Dec 12
Class credits/time to allocate on average per week: 4
CS 192 Fall 2014 Major Project Time Log | Task - What you plan to do | # hours estimated to spend on task | # hours Actually spent on task | Results - what accomplished & comments
Week of 09/14 – 09/20 | Learn object oriented programming in python | 2 | 1 | Basics down, learning more as I go
| Describe outline | 1 | 2 | General outline for classes
| Begin Project | 1 | 1 | Main class working
Week of 09/21 – 9/27 | Improve Outline | 1 | 2 | Revamped much of outline
| Create basic classes | 3 | 2 | Only created 1 class, more developed
Week of 09/28 - 10/04 | Work on chessboard class | 4 | 5 | Major improvements, displayBoard method working properly
Week of 10/05 – 10/11 | Make pieces move | 1 | 1 | Pieces move without a hitch, looking good
| Begin making pieces follow rules | 3 | 2 | Pieces can’t capture own pieces, other minutiae
Week of 10/012– 10/18 | Create rules for piece movement | 4 | 5 | Rook, bishop, queen now move, still some details to work around
Week of 10/19 – 10/25 | Refine piece movement | 4 | 4 | Rook, bishop, queen can’t move through pieces, pawns can move (but can only capture forward)
Week of 11/02 – 11/08 | Finish piece movement | 4 | 3 | Pawns capture correctly, knights and kings move correctly
Week of 11/09 – 11/15
Week of 11/16 – 11/22
Week of 11/23 – 11/29
Week of 11/30 - 12/06
Week of 12/07 - 12/12